## BasicHealthReport_R19MP6
| Cloud |  |  |  |  | BM
| Performance | Serviceablity | Security | RET | NetAct | Performance | Serviceablity | Security | RET | NetAct | MAV
HLR | Planned USTs = 2 Blocked UST = 0 Done UST = 2 |  |  |  |  | Planned USTs = 9 Blocked UST = 0 Done UST = 8 | Planned USTs = 29 Blocked UST = 0 Done UST = 27 |  |  | Planned USTs = 13 Blocked UST = 0 Done UST = 13
HSS | Planned USTs = 9 Blocked UST = 0 Done UST = 7 |  |  |  | Planned USTs = 14 Blocked UST = 0 Done UST = 12 | Planned USTs = 8 Blocked UST = 0 Done UST = 3 | Planned USTs = 30 Blocked UST = 0 Done UST = 28 |  |  | Planned USTs = 12 Blocked UST = 0 Done UST = 12
Nokia HSS |  | Planned USTs = 27 Blocked UST = 0 Done UST = 23
CC HSS
CC HLR
TIAMS | [6 empty] | Planned USTs = 18 Blocked UST = 0 Done UST = 15 |  |  | Planned USTs = 8 Blocked UST = 0 Done UST = 8
CMRepo
5G UDM | [11 empty] | <25/03> VMWare toubleshooting is ongoing. Yet to bring up ZTS
5G ZTS
5G NCM
SDL (3G, 4G, 5G)
Some USTs are Blocked
Less than 30% USTs Done
Less than 70% USTs Done
More than 70% USTs Done

## BasicHealthReport_R20.8
| Cloud |  |  |  |  | BM
| Performance | Serviceablity | Security | RET | NetAct | Performance | Serviceablity | Security | RET | NetAct | MAV
HLR
HSS
Nokia HSS
CC HSS
CC HLR
TIAMS
CMRepo
5G UDM
5G ZTS
5G NCM
SDL (3G, 4G, 5G)
Some USTs are Blocked | [10 empty] | Implicitly Covered
Less than 30% USTs Done | [10 empty] | Implicitly Covered
Less than 70% USTs Done | [10 empty] | Implicitly Covered
More than 70% USTs Done | [10 empty] | Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered
Implicitly Covered

## Details_R20.8
Query | Deployment | Area | Results | Blocked By
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI3 and (component = Performance-HLR or (labels in ("<AREA=performance>") and labels in ("<SUTs=HLR>"))) and labels in ("<DPLY=cloud>") and labels not in ("<PROD=SDL>") | HLR CLOUD | Performance
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI3 and (component = Performance-HSS or (labels in ("<AREA=performance>") and labels in ("<SUTs=HSS>"))) and labels in ("<DPLY=cloud>") and labels not in ("<PROD=SDL>") | HSS CLOUD | Performance | RGSOL-10279, RGSOL-10958, RGSOL-10959, RGSOL-10961, RGSOL-10962, RGSOL-11733, | REG-23197 Critical Open 2020-07-06 [4g-5g-IWF-TADS] : UECM memory leak observed during TADS calls REG-23161 Critical Pending Feedback 2020-07-01 NGC_H2P01 port is not closing when Nokia HSS-VNF is down(CALLP is inactive, HSM down, ICM DOWN,ONE-NDS unavailability) REG-23174 Major Resolved 2020-07-02 NGC_H2P01: Connection down alarm priority needs to be changed REG-23081 Major Reopened 2020-06-18 Outgoing(CLR) requests are failing on FEDS network/connection fluctuation
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI3 and (component = Performance-HSS or (labels in ("<AREA=performance>") and labels in ("<SUTs=HSS>"))) and labels in ("<DPLY=Baremetal>") and labels not in ("<PROD=SDL>") | HSS BM | Performance
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI3 and (component = Performance-HLR or (labels in ("<AREA=performance>") and labels in ("<SUTs=HLR>"))) and labels in ("<DPLY=Baremetal>") and labels not in ("<PROD=SDL>") | HLR BM | Performance | RGSOL-10501, | REG-23207 Critical Open 2020-07-06 20.8: HLR: RTP is not coming up after enabling secure ldap flag.
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-BM or (component = Maintenance-ST and labels not in ("<AREA=performance>") and labels in ("<DPLY=baremetal>"))) and labels in ("<SUTs=HSS>") | HSS BM | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-BM or (component = Maintenance-ST and labels not in ("<AREA=performance>") and labels in ("<DPLY=baremetal>"))) and labels in ("<SUTs=HLR>", "<SUTs=PCC>") | HLR BM | Serviceability | RGSOL-10650, RGSOL-10736, RGSOL-10746, RGSOL-10765, | IMS-87716 Blocker Open 2020-07-06 PCC 20.8 :- PCC Upgrade s failing at rtp start due to "ClmMond" process is not running.
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-Cloud or (component = Maintenance-ST and labels in ("<DPLY=cloud>") and labels not in ("<AREA=performance>"))) and labels not in ("<DPLY=compactCore>") | Nokia HSS | Serviceability | RGSOL-11421, RGSOL-11438, | REG-23206 Major Open 2020-07-06 CNF HSS Deployment is getting re-deployed with same namespace which is already deployed REG-23195 Major Resolved 2020-07-06 CNF HSS Auto Deployment is failed REG-23204 Major Open 2020-07-06 LDAP Load balancer POD to FEDSA distribution is not proper
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-Cloud or (component = Maintenance and labels not in ("<AREA=performance>"))) and labels in ("<DPLY=compactCore>") and labels in ("<SUTs=HSS>") | CC_HSS | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-Cloud or (component = Maintenance and labels not in ("<AREA=performance>"))) and labels in ("<DPLY=compactCore>") and labels in ("<SUTs=HLR>") | CC_HLR | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-BM or (component = Maintenance-ST AND labels in ("<DPLY=baremetal>") )) and summary ~ TIAM | TIAM | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = security and labels in ("<DPLY=baremetal>") and labels in ("<SUTs=HLR>") | HLR BM | Security
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = security and labels in ("<DPLY=baremetal>") and summary ~ TIAM | TIAM | Security
Project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = security and labels in ("<DPLY=baremetal>") and labels not in ("<SUTs=HLR>") and summary !~ TIAM | HSS BM | Security
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = security and labels in ("<DPLY=cloud>") | Nokia HSS | Security
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels = "<SUBA=preMAV>" and labels = "<SUTs=HLR>" | HLR | MAV
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels = "<SUBA=preMAV>" and labels = "<SUTs=HSS>" | HSS | MAV
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels != "<SUBA=preMAV>" and labels = "<SUTs=HLR>" | HLR | RET
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels != "<SUBA=preMAV>" and labels = "<SUTs=HSS>" | HSS | RET
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=cloud>" and labels = "<SUTs=HLR>" and labels != "<SUTs=HSS>" | HLR CLOUD | NetACT
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=cloud>" and labels = "<SUTs=HSS>" | HSS (& combined) CLOUD | NetACT
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary !~ TIAM and labels = "<SUTs=HLR>" | BM HLR | NetACT
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary !~ TIAM and labels = "<SUTs=HSS>" | BM HSS | NetAct
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary ~ TIAM | TIAM | NetACT
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND ((component= 5g-syve and labels in ("<AREA=performance>")) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") and labels in ("<USCS=eoLoad>") ) ) and summary !~ ZTS | 5G | Performance
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND ((component= 5g-syve and labels in ("<AREA=serviceability_operability>")) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") and labels not in ("<USCS=eoLoad>") ) ) and summary !~ ZTS | 5G | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component= 5g-syve and labels in("<NEMS=netAct>") and summary !~ ZTS | 5G | NetACT (Old Labels)
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND ((component= 5g-syve) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") ) ) and summary ~ ZTS | 5G | ZTS (old Labels)
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND ((component= 5g-syve and summary ~ NCM) or (component = Maintenance-ST and labels in ("<PROD=NCM>"))) | 5G | NCM (Old Lables)
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = 5g-syve AND labels in ("<PROD=SDL>") OR component = Maintenance-ST AND labels in ("<PROD=SDL>") OR summary ~ SDL) | SDL | Overall
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = Security and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") | 5G | Security
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels != "<SUBA=preMAV>" and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") | 5G | RET

## Details_R19MP6
Query | Deployment | Area | Results | Blocked By
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI3 and (component = Performance-HLR or (labels in ("<AREA=performance>") and labels in ("<SUTs=HLR>"))) and labels in ("<DPLY=cloud>") and labels not in ("<PROD=SDL>") | HLR CLOUD | Performance
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI3 and (component = Performance-HSS or (labels in ("<AREA=performance>") and labels in ("<SUTs=HSS>"))) and labels in ("<DPLY=cloud>") and labels not in ("<PROD=SDL>") | HSS CLOUD | Performance
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI3 and (component = Performance-HSS or (labels in ("<AREA=performance>") and labels in ("<SUTs=HSS>"))) and labels in ("<DPLY=Baremetal>") and labels not in ("<PROD=SDL>") | HSS BM | Performance
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI3 and (component = Performance-HLR or (labels in ("<AREA=performance>") and labels in ("<SUTs=HLR>"))) and labels in ("<DPLY=Baremetal>") and labels not in ("<PROD=SDL>") | HLR BM | Performance
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-BM or (component = Maintenance-ST and labels not in ("<AREA=performance>") and labels in ("<DPLY=baremetal>"))) and labels in ("<SUTs=HSS>") | HSS BM | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-BM or (component = Maintenance-ST and labels not in ("<AREA=performance>") and labels in ("<DPLY=baremetal>"))) and labels in ("<SUTs=HLR>", "<SUTs=PCC>") | HLR BM | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-Cloud or (component = Maintenance-ST and labels in ("<DPLY=cloud>") and labels not in ("<AREA=performance>"))) and labels not in ("<DPLY=compactCore>") | Nokia HSS | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-Cloud or (component = Maintenance and labels not in ("<AREA=performance>"))) and labels in ("<DPLY=compactCore>") and labels in ("<SUTs=HSS>") | CC_HSS | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-Cloud or (component = Maintenance and labels not in ("<AREA=performance>"))) and labels in ("<DPLY=compactCore>") and labels in ("<SUTs=HLR>") | CC_HLR | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = Serviceability-BM or (component = Maintenance-ST AND labels in ("<DPLY=baremetal>") )) and summary ~ TIAM | TIAM | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = security and labels in ("<DPLY=baremetal>") and labels in ("<SUTs=HLR>") | HLR BM | Security
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = security and labels in ("<DPLY=baremetal>") and summary ~ TIAM | TIAM | Security
Project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = security and labels in ("<DPLY=baremetal>") and labels not in ("<SUTs=HLR>") and summary !~ TIAM | HSS BM | Security
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = security and labels in ("<DPLY=cloud>") | Nokia HSS | Security
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels = "<SUBA=preMAV>" and labels = "<SUTs=HLR>" | HLR | MAV
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels = "<SUBA=preMAV>" and labels = "<SUTs=HSS>" | HSS | MAV
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels != "<SUBA=preMAV>" and labels = "<SUTs=HLR>" | HLR | RET
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels != "<SUBA=preMAV>" and labels = "<SUTs=HSS>" | HSS | RET
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=cloud>" and labels = "<SUTs=HLR>" and labels != "<SUTs=HSS>" | HLR CLOUD | NetACT
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=cloud>" and labels = "<SUTs=HSS>" | HSS (& combined) CLOUD | NetACT
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary !~ TIAM and labels = "<SUTs=HLR>" | BM HLR | NetACT
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary !~ TIAM and labels = "<SUTs=HSS>" | BM HSS | NetAct
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary ~ TIAM | TIAM | NetACT
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND ((component= 5g-syve and labels in ("<AREA=performance>")) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") and labels in ("<USCS=eoLoad>") ) ) and summary !~ ZTS | 5G | Performance
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND ((component= 5g-syve and labels in ("<AREA=serviceability_operability>")) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") and labels not in ("<USCS=eoLoad>") ) ) and summary !~ ZTS | 5G | Serviceability
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component= 5g-syve and labels in("<NEMS=netAct>") and summary !~ ZTS | 5G | NetACT (Old Labels)
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND ((component= 5g-syve) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") ) ) and summary ~ ZTS | 5G | ZTS (old Labels)
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND ((component= 5g-syve and summary ~ NCM) or (component = Maintenance-ST and labels in ("<PROD=NCM>"))) | 5G | NCM (Old Lables)
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND (component = 5g-syve AND labels in ("<PROD=SDL>") OR component = Maintenance-ST AND labels in ("<PROD=SDL>") OR summary ~ SDL) | SDL | Overall
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = Security and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") | 5G | Security
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI3 AND component = RET and labels != "<SUBA=preMAV>" and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") | 5G | RET

## JirasRaised
Don’t remove this Row
Key | Summary | Status | Priority | Fix Version | Created on | Reporter
REG-23081 | Outgoing(CLR) requests are failing on FEDS network/connection fluctuation | Reopened | Major | 20.8 | 2020-06-18 | D, Karthik 5. (Nokia - IN/Bangalore)
REG-23161 | NGC_H2P01 port is not closing when Nokia HSS-VNF is down(CALLP is inactive, HSM down, ICM DOWN,ONE-NDS unavailability) | Pending Feedback | Critical | 20.8 | 2020-07-01 | D, Karthik 5. (Nokia - IN/Bangalore)
REG-23165 | H2p Connections are establishing when HSS/Nokia HSS VNF system is on overload | In Progress | Major | 20.8 | 2020-07-01 | D, Karthik 5. (Nokia - IN/Bangalore)
REG-23166 | 20.9:- UDM password generation not happening for UDMDATASTORE | Resolved | Major | 20.9 | 2020-07-01 | Kumar T, Rakesh (Nokia - IN/Bangalore)
REG-23170 | 20.9:- UDM First Installation failed due to ErrImagePull for lfsclient:1.7.4 but as per package it should be 1.6.2 | Resolved | Blocker | 20.9 | 2020-07-01 | Kumar T, Rakesh (Nokia - IN/Bangalore)
REG-23174 | NGC_H2P01: Connection down alarm priority needs to be changed | Resolved | Major | 20.8 | 2020-07-02 | D, Karthik 5. (Nokia - IN/Bangalore)
IMS-87716 | PCC 20.8 :- PCC Upgrade s failing at rtp start due to "ClmMond" process is not running. | Open | Blocker | 20.8 | 2020-07-06 | Goyal, Deepesh (Nokia - IN/Bangalore)
REG-23195 | CNF HSS Auto Deployment is failed | Resolved | Major | 20.8 | 2020-07-06 | Reddy, Daloka (Nokia - IN/Bangalore)
REG-23197 | [4g-5g-IWF-TADS] : UECM memory leak observed during TADS calls | Open | Critical | 20.9 | 2020-07-06 | Yemineni, Chaitanya (Nokia - IN/Bangalore)
IMS-87729 | 20.8: After reboot OAM ip is not pinging from remote machine in HLR and HSS nodes. | Open | Major | 20.8 | 2020-07-06 | Pasupuleti, Gowthami (Nokia - IN/Bangalore)
REG-23202 | UDM 20.9: HTTPLB POD does not come up during UDMVNF Bringup | Open | Blocker | 20.9 | 2020-07-06 | S, Mohanraj (Nokia - IN/Bangalore)
REG-23203 | 20.8: HLR: DP process is restarting when the CPU consumption is 100% | Open | Major | 20.8 | 2020-07-06 | Pasupuleti, Gowthami (Nokia - IN/Bangalore)
REG-23204 | LDAP Load balancer POD to FEDSA distribution is not proper | Open | Major | 20.8 | 2020-07-06 | Reddy, Daloka (Nokia - IN/Bangalore)
ZTS-1143 | ZTS 20.8 drop1 load APP version still shows 20.5 instead of 20.8 | Resolved | Minor | ZTS 20.8 | 2020-07-06 | Reddy, Daloka (Nokia - IN/Bangalore)
REG-23206 | CNF HSS Deployment is getting re-deployed with same namespace which is already deployed | Open | Major | 20.8 | 2020-07-06 | Reddy, Daloka (Nokia - IN/Bangalore)
REG-23207 | 20.8: HLR: RTP is not coming up after enabling secure ldap flag. | Open | Critical | 20.8 | 2020-07-06 | Pasupuleti, Gowthami (Nokia - IN/Bangalore)
REG-23213 | UHHD port should be down when one NDS is down on application or when retry to HSS fails | Open | Critical | 20.9 | 2020-07-07 | Yemineni, Chaitanya (Nokia - IN/Bangalore)

## sheet1
Query
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND status = Blocked AND fixVersion = 2020PI1 and ( (component = Performance-HLR and labels in ("<DPLY=cloud>") ) OR (component = Maintenance-ST and labels in ("<DPLY=cloud>") and labels in ("<SUTs=HLR>") and labels in ("<SUBA=trafficModel>"))) and summary !~ SDL
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND status = Blocked AND fixVersion = 2020PI1 and ( (component = Performance-HSS and labels in ("<DPLY=cloud>") ) OR (component = Maintenance-ST and labels in ("<DPLY=cloud>") and labels in ("<SUTs=HSS>") and labels in ("<SUBA=trafficModel>"))) and summary !~ SDL
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI1 and ((component = Performance-HSS and labels in ("<DPLY=baremetal>")) or ( component = Maintenance-ST AND labels in ("<DPLY=baremetal>") and labels in("<SUTs=HSS>") and labels in ("<SUBA=trafficModel>") ) ) and status = Blocked
project in (TM_UDM_SolutionTeam) AND issuetype = "User Story" AND fixVersion = 2020PI1 and ((component = Performance-HLR and labels in ("<DPLY=baremetal>")) or ( component = Maintenance-ST AND labels in ("<DPLY=baremetal>") and labels in("<SUTs=HLR>") and labels in ("<SUBA=trafficModel>") ) ) and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND (component = Serviceability-BM or (component = Maintenance-ST and labels in ("<SUBA=serviceability>") and labels in ("<DPLY=baremetal>"))) and labels in ("<SUTs=HSS>") and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND (component = Serviceability-BM or (component = Maintenance-ST and labels in ("<SUBA=serviceability>") and labels in ("<DPLY=baremetal>"))) and labels in ("<SUTs=HLR>", "<SUTs=PCC>") and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND (component = Serviceability-Cloud or (component = Maintenance and labels in ("<DPLY=cloud>") and labels in ("<SUBA=serviceability>"))) and labels not in ("<DPLY=compactCore>") and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND (component = Serviceability-Cloud or (component = Maintenance and labels in ("<SUBA=serviceability>"))) and labels in ("<DPLY=compactCore>") and labels in ("<SUTs=HSS>") AND status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND (component = Serviceability-Cloud or (component = Maintenance and labels in ("<SUBA=serviceability>"))) and labels in ("<DPLY=compactCore>") and labels in ("<SUTs=HLR>") AND status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND (component = Serviceability-BM or (component = Maintenance-ST AND labels in ("<DPLY=baremetal>") )) and summary ~ TIAM and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component = security and labels in ("<DPLY=baremetal>") and labels in ("<SUTs=HLR>") and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component = security and labels in ("<DPLY=baremetal>") and summary ~ TIAM and status = Blocked
Project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component = security and labels in ("<DPLY=baremetal>") and labels not in ("<SUTs=HLR>") and summary !~ TIAM and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component = security and labels in ("<DPLY=cloud>") and status =Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component = RET and labels = "<SUBA=preMAV>" and labels = "<SUTs=HLR>" and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component = RET and labels = "<SUBA=preMAV>" and labels = "<SUTs=HSS>" and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component = RET and labels != "<SUBA=preMAV>" and labels = "<SUTs=HLR>" and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component = RET and labels != "<SUBA=preMAV>" and labels = "<SUTs=HSS>" and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND labels = "<NEMS=netAct>" and labels = "<DPLY=cloud>" and labels = "<SUTs=HLR>" and labels != "<SUTs=HSS>" and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND labels = "<NEMS=netAct>" and labels = "<DPLY=cloud>" and labels = "<SUTs=HSS>" and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary !~ TIAM and labels = "<SUTs=HLR>" and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary !~ TIAM and labels = "<SUTs=HSS>" and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND labels = "<NEMS=netAct>" and labels = "<DPLY=baremetal>" and summary ~ TIAM and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND ((component= 5g-syve and labels in ("<AREA=performance>")) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") and labels in ("<USCS=eoLoad>") ) ) and summary !~ ZTS and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND ((component= 5g-syve and labels in ("<AREA=serviceability_operability>")) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") and labels not in ("<USCS=eoLoad>") ) ) and summary !~ ZTS and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND component= 5g-syve and labels in("<NEMS=netAct>") and summary !~ ZTS and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND ((component= 5g-syve) or (component = Maintenance-ST and labels in ("<SUTs=AUSF>", "<SUTs=UDM>") ) ) and summary ~ ZTS and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND ((component= 5g-syve and summary ~ NCM) or (component = Maintenance-ST and labels in ("<PROD=NCM>"))) and status = Blocked
project in (RGSOL) AND issuetype = "User Story" AND fixVersion = 2020PI1 AND (component = 5g-syve AND labels in ("<PROD=SDL>") OR component = Maintenance-ST AND labels in ("<PROD=SDL>") OR summary ~ SDL) and status = Blocked

## Trends
| Release 20 | [8 empty] | Release 18.5 MP6
Week | Blocked UST Count | Blocked Area count | Performance | Serviceability | Security | RET&MAV | NetACT | 5G | Week | Blocked UST Count | Blocked Area count | Performance | Serviceability | Security | RET&MAV | NetACT | 5G